## Construction Accounting
|  |  | info@vegahomes.lk | CONSTRUCTION ACCOUNTING
www.vegahomes.lk
No 494, Puttalam Road, Kurunegala
+9471 274 1577, +947777 20 888
Project Information |  |  |  |  | Income | Actual | Budget | Variances
Project Name |  | Commercial Office Building |  |  | Contract Amount | 35000000 | 30000000 | 5000000
Project ID |  | VH-001 |  |  | Change Orders | 2500000 | 1000000 | 1500000
Project Manager |  |  |  |  | Progress Payments | 26000000 | 3500000 | 22500000
Project Start Date |  |  |  |  | Retainage Released | 1000000 | 280000 | 720000
Project End Date | [7 empty] | 0
0
Total Actual Income |  |  | Total Actual Expenses | Net Income |  |  |  | 0
0
6250000 |  |  | 5194547 | 1055453 |  |  |  | 0
[5 empty] | Total Income | 64500000 | 34780000 | 29720000
INCOME |  |  |  |  | Expenses | Actual | Budget | Variances
Direct Costs
| Actual | 64500000 |  |  | Labor | 497300 | 48000 | 449300
| Budget | 34780000 |  |  | Materials | 989735 | 32000 | 957735
[5 empty] | Equipment | 26156 | 14000 | 12156
[5 empty] | Subcontractor Costs | 106080 | 18000 | 88080
[5 empty] | Other Direct Costs | 3366026 | 6000 | 3360026
0
0
0
EXPENSES |  |  |  |  | Indirect Costs
[5 empty] | Overhead | 10000 | 9000 | 1000
[5 empty] | Administrative Expenses | 8000 | 7500 | 500
[5 empty] | Insurance | 3000 | 3200 | -200
| Actual | 5008297 |  |  | Permits and Fees | 2000 | 1800 | 200
| Budget | 139500 | [5 empty] | 0
0
0
[5 empty] | Total Expenses | 5008297 | 139500 | 4868797
Note on N9: Variance=Actual Amount−Budgeted Amount
Note on N10: Colored cells have already been formulated
Note on N23: Colored cells have already been formulated

## Sheet1
Sum of Total | Column Labels
Row Labels | Labour | Machinery | Material | Sub Contractor | Transport | Other | Grand Total
3/4" Metal Cube 01 |  |  | 28500 |  |  | 8500 | 37000
6"x9" Struips | [5 empty] | 1190 | 1190
A.C.K Colour House | [5 empty] | 21450 | 21450
A.K.Hardware | [5 empty] | 4500 | 4500
Ajantha(Mason)/Advance | 305800 |  |  |  |  | 900778 | 1206578
Amila(Electrical)/Advance | 61000 | [5 empty] | 61000
Anthony's Hw | [5 empty] | 90230 | 90230
Binding 2Kg | [5 empty] | 800 | 800
Bricks = 3000Nr | [5 empty] | 99000 | 99000
Cainz Hw |  |  | 2150 |  |  | 181651 | 183801
Card Board | [5 empty] | 1500 | 1500
Cement |  |  | 10780 |  |  | 75300 | 86080
Cement Bag 06 Nr |  |  | 12600 |  |  |  | 12600
Central Hw |  |  | 43580 |  |  |  | 43580
Chamidu Timbers |  |  | 6880 |  |  | 2250 | 9130
Chathuranga Hw |  |  | 4510 |  |  | 27240 | 31750
Chuti Mahaththaya |  |  |  | 17500 |  | 50000 | 67500
Dewmith Construction |  |  |  | 34500 |  |  | 34500
Electrical Items | [5 empty] | 1710 | 1710
Excavator |  | 13500 |  |  |  |  | 13500
Finex Engineering |  |  | 5750 |  |  | 71542 | 77292
Foods -Mr.Nazir |  |  |  | 2520 |  |  | 2520
Hardware Item | [5 empty] | 650 | 650
Jagath(Mason)/Salary | [5 empty] | 23200 | 23200
Jagath(Mason)/Salary | 29000 | [5 empty] | 29000
Jagath(Mason)/Salary (Slab Repairing) | 5800 | [5 empty] | 5800
Jayalanka Hw | [5 empty] | 10250 | 10250
Jenerator | [5 empty] | 10800 | 10800
K.S.De Silva and Son | [5 empty] | 4330 | 4330
Lanka Tiles | [5 empty] | 71218 | 71218
Linko Construction |  | 12656 |  |  |  | 100000 | 112656
Lion Plywood |  |  | 38400 |  |  |  | 38400
M City Hw |  |  | 1000 |  |  |  | 1000
M.M Hardware | [5 empty] | 1150 | 1150
Mahagalkadawala Hw |  |  | 286005 |  |  | 90972 | 376977
Manjula(Welder)/Advance | [5 empty] | 15000 | 15000
Modern Hardware |  |  | 3880 |  |  |  | 3880
Mr.Mahiti |  |  |  |  | 5000 |  | 5000
Mr.Nazir |  |  |  | 44000 |  |  | 44000
Mr.Nazir (Advance Payment) |  |  |  | 1000 |  |  | 1000
Mr.Nazir- Foods |  |  |  | 1560 |  |  | 1560
Mr.Nazir-Brick Wall Demolish |  |  |  | 5000 |  |  | 5000
Multi Hw |  |  | 700 |  |  |  | 700
Neel(Tree Cutter) | [5 empty] | 7000 | 7000
Nilu(Mason)/Advance | 1000 |  |  |  |  | 5000 | 6000
Nilu(Mason)/Salary | 85700 |  |  |  |  | 20900 | 106600
Pearl waterproofing solution | [5 empty] | 75000 | 75000
Polythene | [5 empty] | 1200 | 1200
Priyantha(u/sk)/Advance | 1000 | [5 empty] | 1000
Ravi(Painter)/Advance | [5 empty] | 29000 | 29000
Removing Glass Roof | 8000 | [5 empty] | 8000
Ruwan(Tiler)/Advance | [5 empty] | 118300 | 118300
S.M.Metals | [5 empty] | 3600 | 3600
S.N.S.Construction | [5 empty] | 2000 | 2000
Sand Cube 01 |  |  | 45000 |  |  | 69500 | 114500
Sand Cube 02 | [5 empty] | 90000 | 90000
SF Putty | [5 empty] | 5500 | 5500
Sika/Waterproofing | [5 empty] | 415065 | 415065
Site Visit |  |  |  |  | 2500 |  | 2500
Site Visit |  |  |  |  | 29950 |  | 29950
St Anthonys' Hardware |  |  | 500000 |  |  |  | 500000
Star Hw | [5 empty] | 130625 | 130625
Store | [5 empty] | 20000 | 20000
Track Repairing | [5 empty] | 75000 | 75000
Vega (Tools Rent) | [5 empty] | 400475 | 400475
Welagedara Hw | [5 empty] | 32650 | 32650
Transport |  |  |  |  | 171800 |  | 171800
Grand Total | 497300 | 26156 | 989735 | 106080 | 209250 | 3366026 | 5194547
TOTAL RECEIVED | 6250000
TOTAL EXPENSES | 5194547
OUTSTANDING PAYMENTS | 5194547
70% OF TOTAL RECEIVED | 4375000
BALANCE | -6014094

## Accounts
Mr. Lalith Suranga (Millawa/New Works) | [13 empty] | 500000 | 173500 | 0 | 0 | 57500 | 0 | 13500 | 5000 | 4080 | 0 | 0 | 0
INCOME BALANCE STATEMENT
Date | Payment No | Amount | Cumulative | Remarks | Date2 | Entry No | Description | Category | Memo | Stage | BOQ Item | Total | Cumulative2 | Outstanding Payments | Transport | Labour / Sub Contractor | Site Visit | Machinery | Minor Material | Major Material | Service Charge | Utility Bills | Food & Beverages | Fuel | Others
2023-06-30 | 1 | 500000 | 500000 | Cash | 2023-06-14 | 1 | Site Visit | Transport | 06/1103 | Stage-01 | Tile Works | 5000 | 5000 |  | 5000
2023-07-27 | 1 | 500000 | 1000000 | Bank | 2023-06-14 | 2 | Mr.Mahiti | Transport | 06/1104 | Stage-02 | Plastering Works | 5000 | 10000 | [7 empty] | 5000
2023-10-05 | 1 | 500000 | 1500000 | Online | 2023-06-28 | 3 | Mahagalkadawala Hw | Material | 06/1118 | Stage-03 | Painting Works | 8400 | 18400
2023-10-12 | 1 | 500000 | 2000000 | Bank | 2023-06-27 | 4 | Ajantha(Mason)/Advance | Labour | 06/1120 | Stage-04 | Aluminium Works | 5000 | 23400
2023-11-01 | 1 | 1500000 | 3500000 | Online | 2023-06-26 | 5 | Site Visit | Transport | 06/1126 | Stage-05 | Timber Works | 2500 | 25900 |  | 2500
2024-01-20 | 1 | 1000000 | 4500000 | Bank | 2023-06-29 | 6 | Transport | Transport | 06/1129 | Stage-06 | Steel Works | 5000 | 30900 |  | 2500
2024-02-28 | 1 | 700000 | 5200000 | Bank | 2023-06-27 | 7 | Transport | Transport | 06/1130 |  | Waterproofing | 5000 | 35900 |  | 5000
2024-03-11 | 1 | 300000 | 5500000 | Online | 2023-07-01 | 8 | Ajantha(Mason)/Advance | Labour | 06/1141 |  | Roofing | 16300 | 52200
2024-04-07 | 1 | 250000 | 5750000 | Bank | 2023-07-01 | 9 | Removing Glass Roof | Labour | 07/1146 |  | Electrical Works | 8000 | 60200
2024-04-10 | 1 | 500000 | 6250000 | Bank | 2023-07-04 | 10 | Transport | Transport | 07/1146 |  | Masonry Works | 5100 | 65300 |  | 5100
| 1 |  |  |  | 2023-07-04 | 11 | Foods -Mr.Nazir | Sub Contractor | 07/1147 |  | Plumbing Works | 2520 | 67820 | [8 empty] | 2520
| 1 |  |  |  | 2023-07-04 | 12 | Mr.Nazir (Advance Payment) | Sub Contractor | 07/1148 |  | Rain Gutters | 1000 | 68820
| 1 |  |  |  | 2023-07-04 | 13 | Transport | Transport | 07/1149 |  |  | 5000 | 73820 |  | 5000
| 1 |  |  |  | 2023-07-04 | 14 | Chathuranga Hw | Material | 07/1151 |  |  | 3160 | 76980
| 1 |  |  |  | 2023-07-04 | 15 | Multi Hw | Material | 07/1152 |  |  | 700 | 77680
| 1 |  |  |  | 2023-07-05 | 16 | Mr.Nazir-Brick Wall Demolish | Sub Contractor | 07/1154 |  |  | 5000 | 82680
| 1 |  |  |  | 2023-07-05 | 17 | Mr.Nazir | Sub Contractor | 07/1155 |  |  | 44000 | 126680
| 1 |  |  |  | 2023-07-05 | 18 | Transport | Transport | 07/1156 |  |  | 6000 | 132680 |  | 6000
| 1 |  |  |  | 2023-07-05 | 19 | Mr.Nazir- Foods | Sub Contractor | 07/1157 |  |  | 1560 | 134240 | [8 empty] | 1560
| 1 |  |  |  | 2023-07-06 | 20 | Site Visit | Transport | 07/1159 |  |  | 2700 | 136940 |  | 2700
| 1 |  |  |  | 2023-07-08 | 21 | Nilu(Mason)/Salary | Labour | 07/1172 |  |  | 17500 | 154440
| 1 |  |  |  | 2023-07-12 | 22 | Cement | Material | 07/1183 |  |  | 4400 | 158840
| 1 |  |  |  | 2023-07-12 | 23 | Transport | Transport | 07/1184 |  |  | 2500 | 161340 |  | 2500
| 1 |  |  |  | 2023-07-13 | 24 | Nilu(Mason)/Advance | Labour | 07/1191 |  |  | 1000 | 162340
| 1 |  |  |  | 2023-07-15 | 25 | Nilu(Mason)/Salary | Labour | 07/1193 |  |  | 16400 | 178740
| 1 |  |  |  | 2023-07-18 | 26 | Site Visit | Transport | 07/1204 |  |  | 2500 | 181240 |  | 2500
| 1 |  |  |  | 2023-07-20 | 27 | Mahagalkadawala Hw | Material | 07/1211 |  |  | 56580 | 237820
| 1 |  |  |  | 2023-07-20 | 28 | Site Visit | Transport | 07/1215 |  |  | 6750 | 244570 |  | 6750
| 1 |  |  |  | 2023-07-21 | 29 | Priyantha(u/sk)/Advance | Labour | 07/1216 |  |  | 1000 | 245570
| 1 |  |  |  | 2023-07-21 | 30 | Site Visit | Transport | 07/1217 |  |  | 3000 | 248570 |  | 3000
| 1 |  |  |  | 2023-07-22 | 31 | Nilu(Mason)/Salary | Labour | 07/1218 |  |  | 25100 | 273670
| 1 |  |  |  | 2023-07-24 | 32 | Cement Bag 06 Nr | Material | 07/1227 |  |  | 12600 | 286270
| 1 |  |  |  | 2023-07-24 | 33 | Sand Cube 01 | Material | 07/1228 |  |  | 15000 | 301270
| 1 |  |  |  | 2023-07-24 | 34 | 3/4" Metal Cube 01 | Material | 07/1229 |  |  | 9500 | 310770
| 1 |  |  |  | 2023-07-27 | 35 | Ajantha(Mason)/Advance | Labour | 07/1237 |  |  | 2000 | 312770
| 1 |  |  |  | 2023-07-29 | 36 | Ajantha(Mason)/Advance | Labour | 07/1241 |  |  | 41600 | 354370
| 1 |  |  |  | 2023-07-26 | 37 | Linko Construction | Machinery | 07/1242 |  |  | 1000 | 355370
| 1 |  |  |  | 2023-07-27 | 38 | Site Visit | Transport | 07/1247 |  |  | 2500 | 357870 |  | 2500
| 1 |  |  |  | 2023-07-28 | 39 | Site Visit | Transport | 07/1248 |  |  | 2400 | 360270 |  | 2400
| 1 |  |  |  | 2023-07-29 | 40 | Site Visit | Transport | 07/1249 |  |  | 2400 | 362670 |  | 2400
| 1 |  |  |  | 2023-08-05 | 41 | Ajantha(Mason)/Advance | Labour | 07/1252 |  |  | 23300 | 385970
| 1 |  |  |  | 2023-08-05 | 42 | Chuti Mahaththaya | Sub Contractor | 07/1254 |  |  | 17500 | 403470 |  |  |  |  | 17500
| 1 |  |  |  | 2023-08-12 | 43 | Ajantha(Mason)/Advance | Labour | 08/1285 |  |  | 14000 | 417470
| 1 |  |  |  | 2023-08-16 | 44 | Mahagalkadawala Hw | Material | 08/1297 |  |  | 28305 | 445775
| 1 |  |  |  | 2023-08-17 | 45 | Ajantha(Mason)/Advance | Labour | 08/1298 |  |  | 1000 | 446775
| 1 |  |  |  | 2023-08-19 | 46 | Ajantha(Mason)/Advance | Labour | 08/1306 |  |  | 28000 | 474775
| 1 |  |  |  | 2023-08-18 | 47 | Mahagalkadawala Hw | Material | 08/1307 |  |  | 10000 | 484775
| 1 |  |  |  | 2023-08-18 | 48 | Cainz Hw | Material | 08/1308 |  |  | 2150 | 486925
| 1 |  |  |  | 2023-08-21 | 49 | Chathuranga Hw | Material | 08/1329 |  |  | 1350 | 488275
| 1 |  |  |  | 2023-08-26 | 50 | Ajantha(Mason)/Advance | Labour | 08/1337 |  |  | 17400 | 505675
| 1 |  |  |  | 2023-08-28 | 51 | Ajantha(Mason)/Advance | Labour | 08/1355 |  |  | 5000 | 510675
| 1 |  |  |  | 2023-08-28 | 52 | Dewmith Construction | Sub Contractor | 08/1356 |  |  | 34500 | 545175
| 1 |  |  |  | 2023-09-02 | 53 | Ajantha(Mason)/Advance | Labour | 09/1364 |  |  | 11600 | 556775
| 1 |  |  |  | 2023-09-05 | 54 | Central Hw | Material | 09/1375 |  |  | 10100 | 566875
| 1 |  |  |  | 2023-09-06 | 55 | Transport | Transport | 09/1375 |  |  | 750 | 567625 |  | 750
| 1 |  |  |  | 2023-09-04 | 56 | Mahagalkadawala Hw | Material | 09/1381 |  |  | 22015 | 589640
| 1 |  |  |  | 2023-09-07 | 57 | Central Hw | Material | 09/1386 |  |  | 33480 | 623120 | [12 empty] | 0 | 0 | 0 | 0 | 0
| 1 |  |  |  | 2023-09-08 | 58 | Excavator | Machinery | 09/1387 |  |  | 13500 | 636620 | [6 empty] | 13500 | [5 empty] | 0 | 0 | 0 | 0 | 0
| 1 |  |  |  | 2023-09-08 | 59 | Sand Cube 01 | Material | 09/1389 |  |  | 15000 | 651620
| 1 |  |  |  | 2023-09-08 | 60 | 3/4" Metal Cube 01 | Material | 09/1390 |  |  | 9500 | 661120
| 1 |  |  |  | 2023-09-09 | 61 | M City Hw | Material | 09/1405 |  |  | 1000 | 662120
| 1 |  |  |  | 2023-09-09 | 62 | Chamidu Timbers | Material | 09/1408 |  |  | 6880 | 669000
| 1 |  |  |  | 2023-07-21 | 63 | Site Visit | Transport | 09/1431 |  |  | 2700 | 671700 |  | 2700
| 1 |  |  |  | 2023-07-24 | 64 | St Anthonys' Hardware | Material | 09/1432 |  |  | 500000 | 1171700 | 500000 | 2250
| 1 |  |  |  | 2023-07-26 | 65 | Transport | Transport | 09/1433 |  |  | 2250 | 1173950 |  | 2250
| 1 |  |  |  | 2023-09-01 | 66 | Transport | Transport | 09/1434 |  |  | 2250 | 1176200 |  | 2250
| 1 |  |  |  | 2023-09-04 | 67 | Transport | Transport | 09/1435 |  |  | 3150 | 1179350 |  | 3150
| 1 |  |  |  | 2023-09-07 | 68 | Transport | Transport | 09/1436 |  |  | 2400 | 1181750 |  | 2400
| 1 |  |  |  | 2023-09-08 | 69 | Transport | Transport | 09/1437 |  |  | 2400 | 1184150 |  | 2400
| 1 |  |  |  | 2023-09-09 | 70 | Ajantha(Mason)/Advance | Labour | 09/1445 |  |  | 29800 | 1213950
| 1 |  |  |  | 2023-09-16 | 71 | Ajantha(Mason)/Advance | Labour | 09/1450 |  |  | 5800 | 1219750
| 1 |  |  |  | 2023-09-16 | 72 | Jagath(Mason)/Salary (Slab Repairing) | Labour | 09/1457 |  |  | 5800 | 1225550
| 1 |  |  |  | 2023-09-16 | 73 | Ajantha(Mason)/Advance | Labour | 09/1452 |  |  | 6600 | 1232150
| 1 |  |  |  | 2023-09-14 | 74 | Ajantha(Mason)/Advance | Labour | 09/1457 |  |  | 5000 | 1237150
| 1 |  |  |  | 2023-09-13 | 75 | Mahagalkadawala Hw | Material | 09/1460 |  |  | 18680 | 1255830
| 1 |  |  |  | 2023-09-17 | 76 | Ajantha(Mason)/Advance | Labour | 09/1503 |  |  | 14500 | 1270330
| 1 |  |  |  | 2023-09-30 | 77 | Ajantha(Mason)/Advance | Labour | 09/1527 |  |  | 17400 | 1287730
| 1 |  |  |  | 2023-09-29 | 78 | Modern Hardware | Material | 09/1533 |  |  | 3880 | 1291610
| 1 |  |  |  | 2023-09-30 | 79 | Linko Construction | Machinery | 09/1539 |  |  | 8056 | 1299666
| 1 |  |  |  | 2023-09-30 | 80 | Linko Construction | Machinery | 09/1540 |  |  | 3600 | 1303266
| 1 |  |  |  | 2023-10-04 | 81 | Ajantha(Mason)/Advance | Labour | 10/1546 |  |  | 1000 | 1304266
| 1 |  |  |  | 2023-10-04 | 82 | Cement | Material | 10/1550 |  |  | 6380 | 1310646
| 1 |  |  |  | 2023-10-07 | 83 | Ajantha(Mason)/Advance | Labour | 10/1561 |  |  | 5800 | 1316446
| 1 |  |  |  | 2023-10-07 | 84 | Ajantha(Mason)/Advance | Labour | 10/1562 |  |  | 22200 | 1338646
| 1 |  |  |  | 2023-10-07 | 85 | Nilu(Mason)/Salary | Labour | 10/1563 |  |  | 5800 | 1344446
| 1 |  |  |  | 2023-10-07 | 86 | Nilu(Mason)/Salary | Labour | 10/1566 |  |  | 15100 | 1359546
| 1 |  |  |  | 2023-10-09 | 87 | Transport | Transport | 10/1569 |  |  | 2250 | 1361796 |  | 2250
| 1 |  |  |  | 2023-10-14 | 88 | Nilu(Mason)/Salary | Labour | 10/1584 |  |  | 5800 | 1367596
| 1 |  |  |  | 2023-10-14 | 89 | Jagath(Mason)/Salary | Labour | 10/1586 |  |  | 11600 | 1379196
| 1 |  |  |  | 2023-10-08 | 90 | Jagath(Mason)/Salary | Labour | 10/1587 |  |  | 17400 | 1396596
| 1 |  |  |  | 2023-10-14 | 91 | Ajantha(Mason)/Advance | Labour | 10/1588 |  |  | 3500 | 1400096
| 1 |  |  |  | 2023-10-14 | 92 | Ajantha(Mason)/Advance | Labour | 10/1589 |  |  | 29000 | 1429096
| 1 |  |  |  | 2023-10-13 | 93 | Transport | Transport | 10/1590 |  |  | 2500 | 1431596 |  | 2500
| 1 |  |  |  | 2023-10-13 | 94 | Lion Plywood | Material | 10/1594 |  |  | 38400 | 1469996
| 1 |  |  |  | 2023-10-14 | 95 | Mahagalkadawala Hw | Material | 10/1595 |  |  | 142025 | 1612021
| 1 |  |  |  | 2023-10-14 | 96 | Transport | Transport | 10/1596 |  |  | 2000 | 1614021 |  | 2000
| 1 |  |  |  | 2023-10-17 | 97 | Finex Engineering | Material | 10/1601 |  |  | 5750 | 1619771
| 1 |  |  |  | 2023-10-17 | 98 | 3/4" Metal Cube 01 | Material | 10/1605 |  |  | 9500 | 1629271
| 1 |  |  |  | 2023-10-17 | 99 | Sand Cube 01 | Material | 10/1606 |  |  | 15000 | 1644271
| 1 |  |  |  | 2023-10-20 | 100 | Jenerator | Other | 10/1607 |  |  | 10800 | 1655071
| 1 |  |  |  | 2023-10-21 | 101 | Nilu(Mason)/Salary | Other | 10/1610 |  |  | 20900 | 1675971
| 1 |  |  |  | 2023-10-21 | 102 | Ajantha(Mason)/Advance | Other | 10/1611 |  |  | 22100 | 1698071
| 1 |  |  |  | 2023-10-21 | 103 | Jagath(Mason)/Salary | Other | 10/1612 |  |  | 23200 | 1721271
| 1 |  |  |  | 2023-10-18 | 104 | Mahagalkadawala Hw | Other | 10/1616 |  |  | 32720 | 1753991
| 1 |  |  |  | 2023-10-19 | 105 | Chathuranga Hw | Other | 10/1620 |  |  | 1900 | 1755891
| 1 |  |  |  | 2023-10-16 | 106 | K.S.De Silva and Son | Other | 10/1624 |  |  | 2430 | 1758321
| 1 |  |  |  | 2023-11-21 | 107 | Neel(Tree Cutter) | Other | 11/1726 |  |  | 7000 | 1765321
| 1 |  |  |  | 2023-11-22 | 108 | Ajantha(Mason)/Advance | Other | 11/1727 |  |  | 2000 | 1767321
| 1 |  |  |  | 2023-11-25 | 109 | Ajantha(Mason)/Advance | Other | 11/1733 |  |  | 16600 | 1783921
| 1 |  |  |  | 2023-11-28 | 110 | Ajantha(Mason)/Advance | Other | 11/1734 |  |  | 2000 | 1785921
| 1 |  |  |  | 2023-11-28 | 111 | Bricks = 3000Nr | Other | 11/1735 |  |  | 99000 | 1884921
| 1 |  |  |  | 2023-11-28 | 112 | Transport | Transport | 11/1736 |  |  | 15000 | 1899921 |  | 15000
| 1 |  |  |  | 2023-11-28 | 113 | Chuti Mahaththaya | Other | 11/1737 |  |  | 6000 | 1905921 |  |  |  |  | 6000
| 1 |  |  |  | 2023-11-25 | 114 | Chuti Mahaththaya | Other | 11/1740 |  |  | 3000 | 1908921 |  | 3000
| 1 |  |  |  | 2023-11-29 | 115 | Cement | Other | 11/1743 |  |  | 20000 | 1928921
| 1 |  |  |  | 2023-11-29 | 116 | Transport | Transport | 11/1744 |  |  | 3000 | 1931921 |  | 3000
| 1 |  |  |  | 2023-12-02 | 117 | Ajantha(Mason)/Advance | Other | 12/1752 |  |  | 21200 | 1953121
| 1 |  |  |  | 2023-12-01 | 118 | Chathuranga Hw | Other | 12/1754 |  |  | 1700 | 1954821
| 1 |  |  |  | 2023-12-06 | 119 | Ajantha(Mason)/Advance | Other | 12/1771 |  |  | 5000 | 1959821
| 1 |  |  |  | 2023-12-08 | 120 | Ajantha(Mason)/Advance | Other | 12/1783 |  |  | 1000 | 1960821
| 1 |  |  |  | 2023-12-11 | 121 | Cement | Other | 12/1796 |  |  | 2300 | 1963121
| 1 |  |  |  | 2023-12-09 | 122 | Ajantha(Mason)/Advance | Other | 12/1802 |  |  | 62500 | 2025621
| 1 |  |  |  | 2023-12-11 | 123 | Welagedara Hw | Other | 12/1806 |  |  | 19000 | 2044621
| 1 |  |  |  | 2023-12-12 | 124 | Chathuranga Hw | Other | 12/1810 |  |  | 19380 | 2064001
| 1 |  |  |  | 2023-12-11 | 125 | Sand Cube 02 | Other | 12/1811 |  |  | 45000 | 2109001
| 1 |  |  |  | 2023-12-15 | 126 | Ajantha(Mason)/Advance | Other | 12/1832 |  |  | 2000 | 2111001
| 1 |  |  |  | 2023-12-16 | 127 | Ajantha(Mason)/Advance | Other | 12/1838 |  |  | 71100 | 2182101
| 1 |  |  |  | 2023-12-20 | 128 | Nilu(Mason)/Advance | Other | 12/1843 |  |  | 2000 | 2184101
| 1 |  |  |  | 2023-12-19 | 129 | Cement | Other | 12/1848 |  |  | 10000 | 2194101
| 1 |  |  |  | 2023-12-24 | 130 | Ajantha(Mason)/Advance | Other | 12/1859 |  |  | 56000 | 2250101
| 1 |  |  |  | 2023-12-25 | 131 | Cement | Other | 12/1871 |  |  | 10000 | 2260101
| 1 |  |  |  | 2023-12-25 | 132 | Transport | Transport | 12/1881 |  |  | 700 | 2260801 |  | 700
| 1 |  |  |  | 2023-10-14 | 133 | Transport | Transport | 12/1883 |  |  | 4650 | 2265451 |  | 4650
| 1 |  |  |  | 2023-10-25 | 134 | Transport | Transport | 12/1884 |  |  | 8250 | 2273701 |  | 8250
| 1 |  |  |  | 2023-11-22 | 135 | Transport | Transport | 12/1885 |  |  | 2100 | 2275801 |  | 2100
| 1 |  |  |  | 2023-12-06 | 136 | Transport | Transport | 12/1886 |  |  | 8700 | 2284501 |  | 8700
| 1 |  |  |  | 2023-12-21 | 137 | Transport | Transport | 12/1887 |  |  | 10800 | 2295301 |  | 10800
| 1 |  |  |  | 2023-12-28 | 138 | Nilu(Mason)/Advance | Other | 12/1891 |  |  | 3000 | 2298301
| 1 |  |  |  | 2023-12-01 | 139 | Vega (Tools Rent) | Other | 12/1894 |  |  | 262535 | 2560836
| 1 |  |  |  | 2023-12-28 | 140 | Vega (Tools Rent) | Other | 12/1895 |  |  | 87780 | 2648616
| 1 |  |  |  | 2023-12-29 | 141 | Cement | Other | 12/1896 |  |  | 7800 | 2656416
| 1 |  |  |  | 2023-12-30 | 142 | Ajantha(Mason)/Advance | Other | 12/1900 |  |  | 50400 | 2706816
| 1 |  |  |  | 2024-01-04 | 143 | Ajantha(Mason)/Advance | Other | 01/1912 |  |  | 2000 | 2708816
| 1 |  |  |  | 2024-01-06 | 144 | Ajantha(Mason)/Advance | Other | 01/1913 |  |  | 35800 | 2744616
| 1 |  |  |  | 2024-01-09 | 145 | Linko Construction | Other | 01/1920 |  |  | 100000 | 2844616
| 1 |  |  |  | 2024-01-09 | 146 | Chuti Mahaththaya | Other | 01/1923 |  |  | 12000 | 2856616 |  |  |  |  | 12000
| 1 |  |  |  | 2024-01-11 | 147 | Ajantha(Mason)/Advance | Other | 01/1925 |  |  | 7000 | 2863616
| 1 |  |  |  | 2024-01-11 | 148 | Welagedara Hw | Other | 01/1926 |  |  | 5500 | 2869116
| 1 |  |  |  | 2024-01-11 | 149 | SF Putty | Other | 01/1927 |  |  | 5500 | 2874616
| 1 |  |  |  | 2024-01-12 | 150 | Transport | Transport | 01/1928 |  |  | 10050 | 2884666 |  | 10050
| 1 |  |  |  | 2024-01-13 | 151 | Vega (Tools Rent) | Other | 01/1929 |  |  | 50160 | 2934826
| 1 |  |  |  | 2024-01-13 | 152 | Ajantha(Mason)/Advance | Other | 01/1930 |  |  | 24950 | 2959776
| 1 |  |  |  | 2024-01-13 | 153 | Ravi(Painter)/Advance | Other | 01/1931 |  |  | 14000 | 2973776
| 1 |  |  |  | 2024-01-16 | 154 | Transport | Transport | 01/1933 |  |  | 2250 | 2976026 |  | 2250
| 1 |  |  |  | 2024-01-16 | 155 | Welagedara Hw | Other | 01/1934 |  |  | 8150 | 2984176
| 1 |  |  |  | 2024-01-15 | 156 | Cement | Other | 01/1935 |  |  | 2300 | 2986476
| 1 |  |  |  | 2024-01-16 | 157 | Ajantha(Mason)/Advance | Other | 01/1936 |  |  | 10000 | 2996476
| 1 |  |  |  | 2024-01-17 | 158 | A.C.K Colour House | Other | 01/1939 |  |  | 15400 | 3011876
| 1 |  |  |  | 2024-01-18 | 159 | Chuti Mahaththaya | Other | 01/1940 |  |  | 12000 | 3023876 |  |  |  |  | 12000
| 1 |  |  |  | 2024-01-17 | 160 | Ravi(Painter)/Advance | Other | 01/1944 |  |  | 15000 | 3038876
| 1 |  |  |  | 2024-01-19 | 161 | Mahagalkadawala Hw | Other | 01/1945 |  |  | 58252 | 3097128
| 1 |  |  |  | 2024-01-19 | 162 | Cement | Other | 01/1946 |  |  | 18400 | 3115528
| 1 |  |  |  | 2024-01-19 | 163 | Sand Cube 01 | Other | 01/1947 |  |  | 23500 | 3139028
| 1 |  |  |  | 2024-01-20 | 164 | Ajantha(Mason)/Advance | Other | 01/1948 |  |  | 46368 | 3185396
| 1 |  |  |  | 2024-01-22 | 165 | Ajantha(Mason)/Advance | Other | 01/1951 |  |  | 500 | 3185896
| 1 |  |  |  | 2024-01-22 | 166 | Anthony's Hw | Other | 01/1952 |  |  | 36480 | 3222376
| 1 |  |  |  | 2024-01-22 | 167 | 6"x9" Struips | Other | 01/1953 |  |  | 1190 | 3223566
| 1 |  |  |  | 2024-01-24 | 168 | Binding 2Kg | Other | 01/1954 |  |  | 800 | 3224366
| 1 |  |  |  | 2024-01-23 | 169 | Transport | Transport | 01/1955 |  |  | 4000 | 3228366 |  | 4000
| 1 |  |  |  | 2024-01-22 | 170 | Chuti Mahaththaya | Other | 01/1956 |  |  | 10000 | 3238366 |  |  |  |  | 10000
| 1 |  |  |  | 2024-01-24 | 171 | Ajantha(Mason)/Advance | Other | 01/1957 |  |  | 5000 | 3243366
| 1 |  |  |  | 2024-01-24 | 172 | 3/4" Metal Cube 01 | Other | 01/1958 |  |  | 8500 | 3251866
| 1 |  |  |  | 2024-01-23 | 173 | Electrical Items | Other | 01/1959 |  |  | 1710 | 3253576
| 1 |  |  |  | 2024-01-24 | 174 | Cainz Hw | Other | 01/1961 |  |  | 38576 | 3292152
| 1 |  |  |  | 2024-01-24 | 175 | Finex Engineering | Other | 01/1962 |  |  | 5959 | 3298111
| 1 |  |  |  | 2024-01-20 | 176 | Transport | Transport | 01/1964 |  |  | 11100 | 3309211 |  | 11100
| 1 |  |  |  | 2024-01-26 | 177 | S.N.S.Construction | Other | 01/1965 |  |  | 2000 | 3311211
| 1 |  |  |  | 2024-01-26 | 178 | Ajantha(Mason)/Advance | Other | 01/1966 |  |  | 1500 | 3312711
| 1 |  |  |  | 2024-01-27 | 179 | Ajantha(Mason)/Advance | Other | 01/1968 |  |  | 48800 | 3361511
| 1 |  |  |  | 2024-01-29 | 180 | Chathuranga Hw | Other | 01/1971 |  |  | 400 | 3361911
| 1 |  |  |  | 2024-01-29 | 181 | Chathuranga Hw | Other | 01/1972 |  |  | 500 | 3362411
| 1 |  |  |  | 2024-01-29 | 182 | Cainz Hw | Other | 01/1974 |  |  | 21500 | 3383911
| 1 |  |  |  | 2024-01-30 | 183 | Transport | Transport | 01/1975 |  |  | 9150 | 3393061 |  | 9150
| 1 |  |  |  | 2024-01-30 | 184 | Ajantha(Mason)/Advance | Other | 01/1977 |  |  | 2500 | 3395561
| 1 |  |  |  | 2024-02-03 | 185 | Ajantha(Mason)/Advance | Other | 01/1983 |  |  | 39000 | 3434561
| 1 |  |  |  | 2024-02-03 | 186 | Sand Cube 01 | Other | 01/1984 |  |  | 23000 | 3457561
| 1 |  |  |  | 2024-02-03 | 187 | Amila(Electrical)/Advance | Labour | 02/1985 |  |  | 31000 | 3488561
| 1 |  |  |  | 2024-01-06 | 188 | Ajantha(Mason)/Advance | Other | 02/1988 |  |  | 10000 | 3498561
| 1 |  |  |  | 2024-02-08 | 189 | Ajantha(Mason)/Advance | Other | 02/1989 |  |  | 500 | 3499061
| 1 |  |  |  | 2024-02-10 | 190 | Amila(Electrical)/Advance | Labour | 02/1991 |  |  | 30000 | 3529061
| 1 |  |  |  | 2024-02-10 | 191 | Ajantha(Mason)/Advance | Other | 02/1992 |  |  | 29000 | 3558061
| 1 |  |  |  | 2024-02-12 | 192 | Cainz Hw | Other | 02/1994 |  |  | 30530 | 3588591
| 1 |  |  |  | 2024-02-12 | 193 | Finex Engineering | Other | 02/1995 |  |  | 33153 | 3621744
| 1 |  |  |  | 2024-02-12 | 194 | Polythene | Other | 02/1996 |  |  | 1200 | 3622944
| 1 |  |  |  | 2024-02-14 | 195 | Ajantha(Mason)/Advance | Other | 02/1998 |  |  | 2000 | 3624944
| 1 |  |  |  | 2024-02-13 | 196 | Chathuranga Hw | Other | 02/2000 |  |  | 1860 | 3626804
| 1 |  |  |  | 2024-02-17 | 197 | Ajantha(Mason)/Advance | Other | 02/2004 |  |  | 41000 | 3667804
| 1 |  |  |  | 2024-02-20 | 198 | Ajantha(Mason)/Advance | Other | 02/2005 |  |  | 2000 | 3669804
| 1 |  |  |  | 2024-02-22 | 199 | Pearl waterproofing solution | Other | 02/2007 |  |  | 75000 | 3744804
| 1 |  |  |  | 2024-02-24 | 200 | Chathuranga Hw | Other | 02/2009 |  |  | 1500 | 3746304
| 1 |  |  |  | 2024-02-24 | 201 | Ajantha(Mason)/Advance | Other | 02/2010 |  |  | 37500 | 3783804
| 1 |  |  |  | 2024-02-24 | 202 | Cainz Hw | Other | 02/2012 |  |  | 66325 | 3850129
| 1 |  |  |  | 2024-02-24 | 203 | K.S.De Silva and Son | Other | 02/2015 |  |  | 300 | 3850429
| 1 |  |  |  | 2024-02-24 | 204 | K.S.De Silva and Son | Other | 02/2016 |  |  | 1600 | 3852029
| 1 |  |  |  | 2024-03-02 | 205 | Hardware Item | Other | 03/2031 |  |  | 650 | 3852679
| 1 |  |  |  | 2024-03-02 | 206 | Ajantha(Mason)/Advance | Other | 03/2036 |  |  | 15100 | 3867779
| 1 |  |  |  | 2024-02-01 | 207 | Star Hw | Other | 03/2041 |  |  | 34595 | 3902374
| 1 |  |  |  | 2024-02-02 | 208 | Star Hw | Other | 03/2042 |  |  | 76650 | 3979024
| 1 |  |  |  | 2024-02-06 | 209 | Star Hw | Other | 03/2043 |  |  | 7530 | 3986554
| 1 |  |  |  | 2024-02-05 | 210 | Star Hw | Other | 03/2043 |  |  | 11850 | 3998404
| 1 |  |  |  | 2024-03-07 | 211 | Manjula(Welder)/Advance | Other | 03/2053 |  |  | 15000 | 4013404
| 1 |  |  |  | 2024-03-06 | 212 | Sand Cube 01 | Other | 03/2054 |  |  | 23000 | 4036404
| 1 |  |  |  | 2024-03-09 | 213 | Ajantha(Mason)/Advance | Other | 03/2060 |  |  | 15600 | 4052004
| 1 |  |  |  | 2024-03-13 | 214 | Transport | Transport | 03/2079 |  |  | 20000 | 4072004
| 1 |  |  |  | 2024-03-16 | 215 | Ajantha(Mason)/Advance | Other | 03/2088 |  |  | 11600 | 4083604
| 1 |  |  |  | 2024-03-18 | 216 | Chamidu Timbers | Other | 03/2094 |  |  | 2250 | 4085854
| 1 |  |  |  | 2024-03-18 | 217 | Cainz Hw | Other | 03/2095 |  |  | 2140 | 4087994
| 1 |  |  |  | 2024-03-18 | 218 | Transport | Transport | 03/2096 |  |  | 3000 | 4090994
| 1 |  |  |  | 2024-03-13 | 219 | Ajantha(Mason)/Advance | Other | 03/2120 |  |  | 25500 | 4116494
| 1 |  |  |  | 2024-03-29 | 220 | Finex Engineering | Other | 03/2134 |  |  | 1800 | 4118294
| 1 |  |  |  | 2024-03-29 | 221 | Finex Engineering | Other | 03/2135 |  |  | 600 | 4118894
| 1 |  |  |  | 2024-03-28 | 222 | Cainz Hw | Other | 03/2136 |  |  | 1100 | 4119994
| 1 |  |  |  | 2024-03-28 | 223 | Cainz Hw | Other | 03/2139 |  |  | 18470 | 4138464
| 1 |  |  |  | 2024-03-26 | 224 | Cainz Hw | Other | 03/2141 |  |  | 460 | 4138924
| 1 |  |  |  | 2024-03-28 | 225 | Cement | Other | 03/2143 |  |  | 4500 | 4143424
| 1 |  |  |  | 2024-03-25 | 226 | Finex Engineering | Other | 03/2147 |  |  | 14189 | 4157613
| 1 |  |  |  | 2024-03-26 | 227 | Finex Engineering | Other | 03/2148 |  |  | 15841 | 4173454
| 1 |  |  |  | 2024-03-27 | 228 | Ajantha(Mason)/Advance | Other | 03/2150 |  |  | 5000 | 4178454
| 1 |  |  |  | 2024-03-28 | 229 | Sika/Waterproofing | Other | 03/2155 |  |  | 415065 | 4593519
| 1 |  |  |  | 2024-03-30 | 230 | Ajantha(Mason)/Advance | Other | 03/2164 |  |  | 78475 | 4671994
| 1 |  |  |  | 2024-03-25 | 231 | M.M Hardware | Other | 04/2166 |  |  | 800 | 4672794
| 1 |  |  |  | 2024-04-02 | 232 | Transport | Transport | 04/2167 |  |  | 3000 | 4675794
| 1 |  |  |  | 2024-04-02 | 233 | Anthony's Hw | Other | 04/2169 |  |  | 53750 | 4729544
| 1 |  |  |  | 2024-04-02 | 234 | S.M.Metals | Other | 04/2170 |  |  | 3600 | 4733144
| 1 |  |  |  | 2024-04-01 | 235 | Jayalanka Hw | Other | 04/2172 |  |  | 10250 | 4743394
| 1 |  |  |  | 2024-04-03 | 236 | Ruwan(Tiler)/Advance | Other | 04/2174 |  |  | 5000 | 4748394
| 1 |  |  |  | 2024-04-02 | 237 | Sand Cube 02 | Other | 04/2179 |  |  | 45000 | 4793394
| 1 |  |  |  | 2024-04-03 | 238 | A.C.K Colour House | Other | 04/2186 |  |  | 6050 | 4799444
| 1 |  |  |  | 2024-04-05 | 239 | M.M Hardware | Other | 04/2189 |  |  | 350 | 4799794
| 1 |  |  |  | 2024-04-03 | 239 | Lanka Tiles | Other | 04/2192 |  |  | 71218 | 4871012
| 1 |  |  |  | 2024-04-05 | 240 | Transport | Transport | 04/2193 |  |  | 5000 | 4876012
| 1 |  |  |  | 2024-04-03 | 241 | Transport | Transport | 04/2195 |  |  | 2500 | 4878512
| 1 |  |  |  | 2024-04-05 | 242 | Ruwan(Tiler)/Advance | Other | 04/2195 |  |  | 10000 | 4888512
| 1 |  |  |  | 2024-04-06 | 243 | Cainz Hw | Other | 04/2197 |  |  | 450 | 4888962
| 1 |  |  |  | 2024-04-06 | 244 | A.K.Hardware | Other | 04/2198 |  |  | 4500 | 4893462
| 1 |  |  |  | 2024-04-06 | 245 | Card Board | Other | 04/2199 |  |  | 1500 | 4894962
| 1 |  |  |  | 2024-04-06 | 246 | Ajantha(Mason)/Advance | Other | 04/2203 |  |  | 78285 | 4973247
| 1 |  |  |  | 2024-04-07 | 247 | Cainz Hw | Other | 04/2207 |  |  | 1500 | 4974747
| 1 |  |  |  | 2024-04-07 | 248 | Cainz Hw | Other | 04/2208 |  |  | 600 | 4975347
| 1 |  |  |  | 2024-04-06 | 249 | Ruwan(Tiler)/Advance | Other | 04/2209 |  |  | 10000 | 4985347
| 1 |  |  |  | 2024-04-07 | 250 | Ruwan(Tiler)/Advance | Other | 04/2210 | Stage-01 |  | 50000 | 5035347
| 1 |  |  |  | 2024-04-09 | 251 | Store | Other | 04/2214 | Stage-04 |  | 20000 | 5055347
| 1 |  |  |  | 2024-04-10 | 252 | Ruwan(Tiler)/Advance | Other | 04/2217 |  |  | 43300 | 5098647
| 1 |  |  |  | 2024-04-10 | 253 | Ajantha(Mason)/Advance | Other | 04/2221 |  |  | 13900 | 5112547
| 1 |  |  |  | 2024-04-10 | 254 | Chuti Mahaththaya | Other | 04/2222 |  |  | 7000 | 5119547
| 1 |  |  |  | 2024-02-22 | 255 | Track Repairing | Other | 02/2267 |  |  | 75000 | 5194547
|  | 6250000 | 6250000 | [8 empty] | 5194547 | 5194547 | 5194547
SAMPLE